## Sheet1
Action items | Date Tentative
Get basic repository set up and a local copy hosted | 2015-03-02
Decide on a design for all the pages(text messages, buttons etc.) | 2015-05-02
Have a basic frame implemented | 2015-06-02
Ensure dynamic frame creation | 2015-08-02
Implement polygon input from user and rendering | 2015-10-02
Ensure test cases for polygon are correctly working and make any improvements | 2015-11-02
Implement raster filling of polygons | 2015-12-02
Ensure all test cases are working good and fix any bugs | 14/2/2015
Create a presentation of the work | 18/2/2015